## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Register | Personal User | Create an account | I can login with my own account to access the mobile application | - Username must not contain spaces and not be accented - Password must be > 8 characters, < 16 characters include uppercase letters, lowercase letters, numbers and special characters. |  | 3 |  |  |  | 1 | 30
PB02 | Login | Personal User | Login to mobile application | I can start to conduct a new survey or continue the unfinished survey | - Login with facebook and gmail - Input data to enter: + Username accepted + Password accepted |  | 3 |  |  |  | 1 | 30
PB03 | Log out | Personal User | Log out from the currently account | I can exit my account whenever I want | - Click the "log out" button - Exit from the currently account |  | 3 |  |  |  | 1 | 5
PB04 | Forgot password | Personal User | Recover password when forgot | I can change my password into the new one and get my account back | - Click "Quên mật khẩu?" - Use the link sent to the account's email which is registered in the profile to change the new password |  | 2 |  |  |  | 1 | 10
PB05 | Edit profile | Personal User | Edit my public profile | I can edit my personal information | - Allow users to edit any personal information they want |  | 1 |  |  |  | 3 | 10
PB06 | Conduct a new survey | Personal User | Conduct a new pollution survey | I can start to make a new pollution survey using mobile application | - Allow users to take the pollution photo sent to AI - The pollution form will be filled automatically based on the AI return result - Allow users to re-check the survey or provide additional information before they move to the next step |  | 3 |  |  |  | 2 | 30
PB07 | Submit survey | Personal User | Submit the pollution survey | I can submit my survey to the server | - Allows users to submit their pollution survey to the server |  | 3 |  |  |  | 3 | 20
PB08 | Save unfinished survey | Personal User | Save my unfinished survey | I can finish my survey another time | - Allow user to save the survey that is not yet ready to submit |  | 3 |  |  |  | 2 | 30
PB09 | Continue unfinished survey | Personal User | Continute my unfinish survey | I can finish my survey and sent it to server | - Allow user to continue edit the survey that is not yet ready to submit |  | 3 |  |  |  | 3 | 30
PB10 | Delete unfinished survey | Personal User | Delete unfinished survey | I can delete my unfinished survey | - Allow user to delete the survey that is not needed to submit |  | 2 |  |  |  | 3 | 30
PB11 | View finished survey | Personal User | View all my finished surveys | I can view my survey history | - Allow users to view all the surveys that they did and submitted to the server |  | 1 |  |  |  | 3 | 30
PB12 | Change language | Personal User | Change the mobile application | I can change the application to different languages | - Allow users to change the language of the application from Vietnam to English and vice versa |  | 1 |  |  |  | 3 | 30
PB13 | Detect pollution types | Personal User | Detect pollution types automatically form input photo | I get pollution types automatically and without going through a combersome process | - An AI will use the input pollution photo to predict the pollution types |  | 3 |  |  |  | 3 | 50
Note on M7: ====== ID#AAAAeu_Dblk jan samuelsson (2022-08-23 14:14:25) Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.

## Main
Project | [5 empty] | Sprint Plan |  | Project Craft Village Pollution Monitor System
Id | Description | Start | End | Status | Remarks | Sprint # | Start | End | Status | Work / Estimates Committed | Work spent Delivered | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 | 2022-09-01 | 2022-09-15 | Complete | 24 | 24
[6 empty] | 2 | 2022-09-17 | 2022-10-01 | Complete | 16 | 16
[6 empty] | 3 | 2022-10-03 | 2022-10-17 | Complete | 27 | 25
[6 empty] | 4 | 2022-10-19 | 2022-11-02 | In Progress
Formulas:
End = [Start]+14
Start = [End, row above]+2

## Sprint 1 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1.1 |  | Sprint 1 Backlog | All Members | Done | 5 | 5 | 0 | 3 | -2 | Day 1: 5
1.2 |  | Design Database | Phuc | Done | 5 | 5 | 0 | 4 | -1 | Day 1: 5
1.3 |  | Database Design Document | Phuc | Done | 3 | 3 | 0 | 2 | -1 | Day 2: 3
1.4 |  | Architecture Document | Ca, Huy | Done | 10 | 10 | 0 | 8 | -2 | Day 2: 10
1.5 |  | Write Test Cases | Trung | Done | 10 | 10 | 0 | 8 | -2 | Day 2: 10
1.6 | PB02 | [FE] Design UX/UI Login Page | Ca | Done | 5 | 5 | 0 | 3 | -2 | Day 2: 5
1.7 | PB02 | [FE] Code UX/UI Login Page | Ca | Done | 10 | 10 | 0 | 8 | -2 | Day 4: 10
1.8 | PB02 | [BE] Code Login Function | Phuc | Done | 10 | 10 | 0 | 8 | -2 | Day 3: 10
1.8 | PB02 | Test and Fix Bug Login Function | Ca, Trung | Done | 5 | 5 | 0 | 4 | -1 | Day 5: 5
1.9 | PB01 | [FE] Design UX/UI Register Page | Ca | Done | 5 | 5 | 0 | 4 | -1 | Day 6: 5
1.10 | PB01 | [FE] Code UX/UI Register Page | Ca | Done | 10 | 10 | 0 | 15 | 5 | Day 9: 10
1.11 | PB01 | [BE] Code Register Function | Phuc | Done | 10 | 10 | 0 | 12 | 2 | Day 8: 10
1.12 | PB01 | Test and Fix Bug Register Function | Ca, Trung | Done | 5 | 5 | 0 | 5 | 0 | Day 10: 5
1.13 | PB03 | [FE] Code UX/UI Logout Function | Ca | Done | 3 | 3 | 0 | 2 | -1 | Day 11: 3
1.14 | PB03 | Test Register Function | Ca, Trung | Done | 2 | 2 | 0 | 1 | -1 | Day 11: 2
1.15 | PB04 | [FE] Design UX/UI Forgot Password Page | Ca | Done | 5 | 5 | 0 | 2 | -3 | Day 12: 5
1.16 | PB04 | [FE] Code UX/UI Forgot Password Page | Ca | Done | 10 | 10 | 0 | 5 | -5 | Day 13: 10
1.17 | PB04 | [BE] Code Forgot Password Function | Phuc | Done | 10 | 10 | 0 | 4 | -6 | Day 12: 10
1.18 | PB04 | Test and Fix Bug Forgot Password Function | Trung | Done | 5 | 5 | 0 | 2 | -3 | Day 14: 5
1.19 | PB02 | [FE] Design Homepage | Ca | Done | 5 | 5 | 0 | 3 | -2 | Day 13: 5
1.20 | PB02 | [FE] Code UX/UI Homepage | Ca | Done | 10 | 10 | 0 | 6 | -4 | Day 14: 10
1.21 | PB13 | [AI] Crawl Trainning Data | Huy, Trung | Done | 20 | 20 | 0 | 15 | -5 | Day 4: 20
1.22 | PB13 | [AI] Build Data Set | Huy, Trung | Done | 10 | 10 | 0 | 8 | -2 | Day 6: 10
1.23 | PB13 | [AI] Train Machine Learning Model | Huy | Done | 10 | 10 | 0 | 10 | 0 | Day 9: 10
1.24 | PB13 | [AI] Deploy Machine Learning Model | Huy | Done | 10 | 10 | 0 | 10 | 0 | Day 13: 10
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
|  |  |  | Total | 193 | 193 | 0 | 152 | -41 | 10 | 28 | 10 | 30 | 5 | 15 | 0 | 10 | 20 | 5 | 5 | 15 | 25 | 15
|  |  |  | Burn down | [5 empty] | 183 | 155 | 145 | 115 | 110 | 95 | 95 | 85 | 65 | 60 | 55 | 40 | 15 | 0
|  |  |  | Burn up | [5 empty] | 10 | 38 | 48 | 78 | 83 | 98 | 98 | 108 | 128 | 133 | 138 | 153 | 178 | 193
|  |  |  | Ideal Burn down | [5 empty] | 179.2143 | 165.4286 | 151.6429 | 137.8571 | 124.0714 | 110.2857 | 96.5 | 82.7143 | 68.9286 | 55.1429 | 41.3571 | 27.5714 | 13.7857 | 0
|  |  |  | Ideal Burn up | [5 empty] | 0 | 13.7857 | 27.5714 | 41.3571 | 55.1429 | 68.9286 | 82.7143 | 96.5 | 110.2857 | 124.0714 | 137.8571 | 151.6429 | 165.4286 | 179.2143
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 2 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1.1 |  | Sprint 2 Backlog | All Members | Done | 5 | 5 | 0 | 6 | 1 | Day 1: 5
1.2 |  | Design Database | Phuc | Done | 5 | 5 | 0 | 5 | 0 | Day 1: 5
1.3 |  | Database Design Document | Phuc | Done | 5 | 5 | 0 | 4 | -1 | Day 2: 5
1.4 |  | Architecture Document | Ca, Huy | Done | 10 | 10 | 0 | 10 | 0 | Day 3: 10
1.5 |  | Write Test Cases | Trung | Done | 10 | 10 | 0 | 10 | 0 | Day 3: 10
1.6 | PB06 | [FE] Design UX/UI Survey Page | Ca | Done | 5 | 5 | 0 | 8 | 3 | Day 3: 5
1.7 | PB06 | [FE] Code UX/UI Survey Page | Ca | Done | 15 | 15 | 0 | 20 | 5 | Day 8: 15
1.8 | PB06 | [BE] Code Survey Function | Phuc | Done | 20 | 20 | 0 | 17 | -3 | Day 9: 20
1.8 | PB06 | Test and Fix Bug Survey Function | Ca, Trung | Done | 15 | 15 | 0 | 25 | 10 | Day 14: 15
1.9 | PB06 | [AI] Write API Machine Learning | Huy | Done | 5 | 5 | 0 | 5 | 0 | Day 8: 5
1.10 | PB13 | [AI] Crawl More Trainning Data | Huy, Trung | Done | 20 | 20 | 0 | 15 | -5 | Day 3: 20
1.11 | PB13 | [AI] Re-build Data Set | Huy, Trung | Done | 20 | 20 | 0 | 12 | -8 | Day 6: 20
1.12 | PB13 | [AI] Train Improve Machine Learning Model | Huy | Done | 10 | 10 | 0 | 5 | -5 | Day 8: 10
1.13 | PB13 | [AI] Deploy New Machine Learning Model | Huy | Done | 5 | 5 | 0 | 5 | 0 | Day 10: 5
1.14 | PB08 | [FE] Code UX/UI Save Survey Page | Ca, Trung | Done | 10 | 10 | 0 | 10 | 0 | Day 3: 10
1.15 | PB08 | [BE] Code Save Survey Function | Phuc | Done | 10 | 10 | 0 | 8 | -2 | Day 5: 10
1.16 | PB08 | Test and Fix Bug Survey Function | Ca, Trung | Done | 10 | 10 | 0 | 6 | -4 | Day 7: 10
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
|  |  |  | Total | 180 | 180 | 0 | 171 | -9 | 10 | 5 | 55 | 0 | 10 | 20 | 10 | 30 | 20 | 5 | 0 | 0 | 0 | 15
|  |  |  | Burn down | [5 empty] | 170 | 165 | 110 | 110 | 100 | 80 | 70 | 40 | 20 | 15 | 15 | 15 | 15 | 0
|  |  |  | Burn up | [5 empty] | 10 | 15 | 70 | 70 | 80 | 100 | 110 | 140 | 160 | 165 | 165 | 165 | 165 | 180
|  |  |  | Ideal Burn down | [5 empty] | 167.1429 | 154.2857 | 141.4286 | 128.5714 | 115.7143 | 102.8571 | 90 | 77.1429 | 64.2857 | 51.4286 | 38.5714 | 25.7143 | 12.8571 | 0
|  |  |  | Ideal Burn up | [5 empty] | 0 | 12.8571 | 25.7143 | 38.5714 | 51.4286 | 64.2857 | 77.1429 | 90 | 102.8571 | 115.7143 | 128.5714 | 141.4286 | 154.2857 | 167.1429
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 3 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1.1 |  | Sprint 3 Backlog | All Members | Done | 5 | 5 | 0 | 3 | -2 | Day 1: 5
1.2 |  | Design Database | Phuc | Done | 5 | 5 | 0 | 3 | -2 | Day 1: 5
1.3 |  | Database Design Document | Phuc | Done | 5 | 5 | 0 | 4 | -1 | Day 2: 5
1.4 |  | Architecture Document | Ca, Huy | Done | 10 | 10 | 0 | 5 | -5 | Day 2: 10
1.5 |  | Write Test Cases | Trung | Done | 10 | 10 | 0 | 10 | 0 | Day 2: 10
1.6 | PB07 | [FE] Code UX/UI Submit Survey Function | Ca | Done | 10 | 10 | 0 | 15 | 5 | Day 4: 10
1.7 | PB07 | [BE] Code Login Submit Survey Function | Phuc | Done | 10 | 10 | 0 | 10 | 0 | Day 4: 10
1.8 | PB07 | Test and Fix Bug Login Function | Ca, Trung | Done | 10 | 10 | 0 | 12 | 2 | Day 7: 10
1.8 | PB09 | [FE] Design UX/UI Continue Survey Page | Trung | Done | 5 | 5 | 0 | 5 | 0 | Day 5: 5
1.9 | PB09 | [FE] Code UX/UI Continue Survey Function | Ca | Done | 10 | 10 | 0 | 8 | -2 | Day 6: 10
1.10 | PB09 | [BE] Code Continue Survey Function | Phuc | Done | 10 | 10 | 0 | 7 | -3 | Day 8: 10
1.11 | PB09 | Test and Fix Bug Continue Survey | Ca, Trung | Done | 5 | 5 | 0 | 5 | 0 | Day 8: 5
1.12 | PB10 | [FE] Code UX/UI Delete Survey Function | Ca | Done | 10 | 10 | 0 | 10 | 0 | Day 7: 10
1.13 | PB10 | [BE] Code Delete Survey Function | Phuc | Done | 10 | 10 | 0 | 8 | -2 | Day 9: 10
1.14 | PB10 | Test and Fix Bug Delete Survey Function | Ca, Trung | Done | 10 | 10 | 0 | 6 | -4 | Day 10: 10
1.15 | PB11 | [FE] Design UX/UI View Survey Page | Trung | Done | 5 | 5 | 0 | 5 | 0 | Day 11: 5
1.16 | PB11 | [FE] Code UX/UI View Survey Page | Trung | Done | 10 | 10 | 0 | 10 | 0 | Day 12: 10
1.17 | PB11 | [BE] Code View Survey Page Function | Phuc | Done | 10 | 10 | 0 | 9 | -1 | Day 12: 10
1.18 | PB11 | Test and Fix Bug View Survey Page | Ca | Done | 5 | 10 | -5 | 10 | 5 | Day 13: 5
1.19 | PB05 | [FE] Design UX/UI Edit Information Page | Ca | Done | 5 | 5 | 0 | 0 | -5 | Day 11: 5
1.20 | PB05 | [FE] Code UX/UI Edit Information Page | Ca | Done | 10 | 10 | 0 | 0 | -10 | Day 12: 10
1.21 | PB05 | [BE] Code View Edit Information Page | Phuc | Done | 10 | 10 | 0 | 0 | -10 | Day 14: 10
1.22 | PB05 | Test and Fix Bug View Survey Page | Trung | Done | 5 | 5 | 0 | 0 | -5 | Day 14: 5
1.23 | PB12 | [FE] Code View Change Language Function | Ca, Trung | In Progress | 15 | 10 | 5 | 0 | -15
1.24 | PB12 | Test and Fix Change Language Function | Ca, Trung | Not Started | 15 | 0 | 15 | 0 | -15
1.25 | PB13 | [AI] Crawl Trainning Data | Huy, Trung | Done | 20 | 20 | 0 | 0 | -20 | Day 4: 20
1.26 | PB13 | [AI] Build Data Set | Huy, Trung | Done | 20 | 20 | 0 | 0 | -20 | Day 8: 20
1.27 | PB13 | [AI] Train Machine Learning Model | Huy | Done | 10 | 10 | 0 | 0 | -10 | Day 12: 10
[6 empty] | 0 | 0 | 0 | 0
|  |  |  | Total | 265 | 250 | 15 | 145 | -120 | 10 | 25 | 0 | 40 | 5 | 10 | 20 | 35 | 10 | 10 | 10 | 40 | 5 | 15
|  |  |  | Burn down | [5 empty] | 255 | 230 | 230 | 190 | 185 | 175 | 155 | 120 | 110 | 100 | 90 | 50 | 45 | 30
|  |  |  | Burn up | [5 empty] | 10 | 35 | 35 | 75 | 80 | 90 | 110 | 145 | 155 | 165 | 175 | 215 | 220 | 235
|  |  |  | Ideal Burn down | [5 empty] | 246.0714 | 227.1429 | 208.2143 | 189.2857 | 170.3571 | 151.4286 | 132.5 | 113.5714 | 94.6429 | 75.7143 | 56.7857 | 37.8571 | 18.9286 | 0
|  |  |  | Ideal Burn up | [5 empty] | 0 | 18.9286 | 37.8571 | 56.7857 | 75.7143 | 94.6429 | 113.5714 | 132.5 | 151.4286 | 170.3571 | 189.2857 | 208.2143 | 227.1429 | 246.0714
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms