## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Register | Personal User Household | Create an account | I can login with my own account to access the mobile application/web application | - Username must not contain spaces and not be accented - Password must be >= 6 characters |  | 3 |  |  |  | 1, 2, 3 | 30 |  |  | Done
PB02 | Authenticate | Personal User Household Authority Admin | Login/Logout to mobile application/web application | I can start to conduct a new survey/provide the information about the craft village | - Login with registed account |  | 3 |  |  |  | 2, 5 | 100 |  |  | Done
PB03 | Authorize | Personal User Household Authority Admin | Login/Logout according to the role that has been registed | I can perform the task correctly according to the role | - Login with registed account and perform task according to the registed role |  | 3 |  |  |  | 2 | 100 |  |  | Done
PB04 | Password Recovery | Personal User | Recover password when forgot | I can change my password into the new one and get my account back | - Use the code that sent to the account's email which is registered in the profile to change the new password |  | 2 |  |  |  | 2 | 20 |  |  | Done
PB05 | Edit Profile | Personal User Household Local authority Admin | Edit my profile | I can edit my personal information | - Allow users to edit any personal information they want |  | 2 |  |  |  | 2 | 20 |  |  | Done
PB06 | Create Local Authority Account | Admin | Create an local authority account | I can provide the account to the local authority user to manage their local craft village | - Allow the admin to create the a local authority account - Login with registed account | [5 empty] | 3 | 30 |  |  | Done
PB07 | Change Password | Personal User Household Authority Admin | Change my old password into a new password | Next time I can login using my new password and protect my account in case of password leak | - Allow user to click "Thay đổi mật khẩu" and change their current password to a new password |  | 3 |  |  |  | 2 | 30 |  |  | Done
PB08 | Conduct a new pollution survey | Personal User | Conduct a new pollution survey automatically | I can perform a quick and efficent pollution survey that contain all the information such as pollution types, location, additional information of that craft village | - Allow users to take the pollution photo sent to AI - The pollution form will be filled automatically based on the AI return result - Allow users to re-check the survey or provide additional information before they move to the next step |  | 3 |  |  |  | 3, 5 | 200 |  |  | Done
PB09 | Request New Village | Personal User Household | Add a new village that does not exsit on the database | I can submit a pollution survey about that new craft village that exist real life but does not exist in the database | - Allow the user to add a new craft village to the database |  | 3 |  |  |  | 2, 4, 5 | 30 |  |  | Done
PB10 | Accept/Decline/Add New Village | Local Authority | Accept/Decline a new village that has been submit by a personal user | I can protect the integrity of the craft village data from fault information | - Allow user to accepct or decline the new village that submitted by a personal user and that village belong to their management |  | 3 |  |  |  | 4 | 20 |  |  | Done
PB11 | Change language | Personal User | Change the language of the mobile | The application language change from Vietnamese to English and vice versa | - Allow users to change the language of the application from Vietnamese to English and vice versa |  | 1 |  |  |  | 2, 5 | 20 |  |  | Done
PB12 | View finished/in progess survey | Personal User | View all the survey that I had conducted that finished/in progess | I know how many and which craft village that I had conducted the survey | - Allow users to view all the surveys that they did and submitted to the server |  | 2 |  |  |  | 4 | 10 |  |  | Done
PB13 | Pollution Detection AI | Personal User | Have an AI with the ability to detect the pollution types from an image automatically and acurately | The application can detect pollutions types automatically with a quick and accureate respone | - Allow user to submit pollution photo and the AI will detect pollution types then sent back to the application |  | 3 |  |  |  | 1, 2, 3, 4, 5 | 400 |  |  | Done
PB14 | View dashboard | Local Authority | See the number of new household or new survey in month. And view new village request or total village | I know how many survey, new household or new village request each month | - Allow user to view the number of new household, new survey, village request in month anh total village |  | 3 |  |  |  | 3, 5 | 30 |  |  | Done
PB15 | Declare household info | Household | Declare my village I am living and send request if my village does not exist | I can let authority know which village I belong to | - Allow user declare village and request new village |  | 3 |  |  |  | 3 | 30 |  |  | Done
Note on M7: ====== ID#AAAAeu_Dblk jan samuelsson (2022-08-23 14:14:25) Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.

## Main
Project | [5 empty] | Sprint Plan |  | Project Craft Village Pollution Monitor System
Id | Description | Start | End | Status | Remarks | Sprint # | Start | End | Status | Work / Estimates Committed | Work spent Delivered | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 | 2022-09-01 | 2022-09-15 | Complete
[6 empty] | 2 | 2022-09-18 | 2022-10-02 | Complete
[6 empty] | 3 | 2022-10-05 | 2022-10-19 | Complete
[6 empty] | 4 | 2022-10-22 | 2022-11-05 | Complete
[6 empty] | 5 | 2022-11-08 | 2022-11-22 | Complete
Formulas:
End = [Start]+14
Start = [End, row above]+3

## Sprint 1 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1.1 | PB01 | [FE] Design UX/UI Register Page For Mobile Application | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 3: 8
1.2 | PB01 | [FE] Code UX/UI Register Page For Mobile Application | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 4: 8
1.3 | PB01 | [FE] Code Register Function For Mobile Application | Ca | Done | 12 | 12 | 0 | 8 | -4 | Day 6: 12
1.4 | PB09 | [DB + BE] Create Database (AD_COUNTRY, AD_PROVINCE, AD_DISTRICT, VILLAGE) and Mapping entities | Phuc | Done | 10 | 10 | 0 | 8 | -2 | Day 3: 10
1.5 | PB09 | [DB] Crawl Data For Database (AD_COUNTRY, AD_PROVINCE, AD_DISTRICT, VILLAGE) | Trung | Done | 40 | 40 | 0 | 40 | 0 | Day 14: 40
1.6 | PB01 | [FE] Design Web layout | Phuc | Done | 12 | 12 | 0 | 8 | -4 | Day 4: 12
1.7 | PB02 | [FE] Design UX/UI Login Page For Mobile Application | Trung | Done | 8 | 8 | 0 | 8 | 0 | Day 3: 8
1.8 | PB02 | [FE] Design UX/UI Home Page For Mobile Application | Trung | Done | 8 | 8 | 0 | 12 | 4 | Day 4: 8
1.9 | PB02 | [FE] Code UX/UI Login Page For Mobile Application | Ca | Done | 12 | 12 | 0 | 8 | -4 | Day 9: 12
1.10 | PB02 | [FE] Code UX/UI Home Page For Mobile Application | Ca | Done | 12 | 12 | 0 | 10 | -2 | Day 12: 12
1.11 | PB02 | [FE] Code Login Function For Mobile Application | Ca | Done | 8 | 8 | 0 | 10 | 2 | Day 10: 8
1.12 | PB02 | [FE] Code Logout Function For Mobile Application | Ca | Done | 3 | 3 | 0 | 2 | -1 | Day 13: 3
1.13 | PB02 | [BE] Code Address API | Phuc | Done | 6 | 12 | -6 | 8 | 2 | Day 9: 6
1.14 | PB02 | [BE] Code Village API | Phuc | Done | 9 | 3 | 6 | 2 | -7 | Day 10: 9
1.15 | PB13 | [AI] Research Method To Build AI | Huy | Done | 26 | 26 | 0 | 26 | 0 | Day 6: 26
1.16 | PB13 | [AI] Crawl Data For AI | Huy | Done | 26 | 26 | 0 | 26 | 0 | Day 13: 26
|  |  |  | Total | 208 | 208 | 0 | 192 | -16 | 0 | 0 | 26 | 28 | 0 | 38 | 0 | 0 | 18 | 17 | 0 | 12 | 29 | 40
|  |  |  | Burn down | [5 empty] | 208 | 208 | 182 | 154 | 154 | 116 | 116 | 116 | 98 | 81 | 81 | 69 | 40 | 0
|  |  |  | Burn up | [5 empty] | 0 | 0 | 26 | 54 | 54 | 92 | 92 | 92 | 110 | 127 | 127 | 139 | 168 | 208
|  |  |  | Ideal Burn down | [5 empty] | 193.1429 | 178.2857 | 163.4286 | 148.5714 | 133.7143 | 118.8571 | 104 | 89.1429 | 74.2857 | 59.4286 | 44.5714 | 29.7143 | 14.8571 | 0
|  |  |  | Ideal Burn up | [5 empty] | 0 | 14.8571 | 29.7143 | 44.5714 | 59.4286 | 74.2857 | 89.1429 | 104 | 118.8571 | 133.7143 | 148.5714 | 163.4286 | 178.2857 | 193.1429
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 2 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
2.1 | PB04 | [FE] Design UX/UI Forget Password Page For Mobile Application | Ca | Done | 4 | 4 | 0 | 4 | 0 | Day 1: 4
2.2 | PB04 | [FE] Code UX/UI Forget Password Page For Mobile Application | Ca | Done | 4 | 4 | 0 | 4 | 0 | Day 1: 4
2.3 | PB04 | [FE] Code Forget Password Function For Mobile Application | Ca | Done | 3 | 3 | 0 | 3 | 0 | Day 2: 3
2.4 | PB04 | [BE] Code Forget Password Function API | Phuc | Done | 4 | 4 | 0 | 3 | -1 | Day 1: 4
2.5 | PB07 | [FE] Design UX/UI Change Password Page For Mobile Application | Ca | Done | 4 | 4 | 0 | 4 | 0 | Day 4: 4
2.6 | PB07 | [FE] Code UX/UI Change Password Page For Mobile Application | Ca | Done | 4 | 4 | 0 | 4 | 0 | Day 6: 4
2.7 | PB07 | [FE] Code Change Password Function For Mobile Application | Ca | Done | 8 | 8 | 0 | 4 | -4 | Day 2: 8
2.8 | PB07 | [BE] Code Change Password Function API | Phuc | Done | 4 | 4 | 0 | 4 | 0 | Day 3: 4
2.9 | PB01 | [FE] Design UX/UI Register Page For Web Application | Trung | Done | 8 | 8 | 0 | 8 | 0 | Day 1: 8
2.10 | PB01 | [FE] Code UX/UI Register Page For Web Application | Trung | Done | 8 | 8 | 0 | 8 | 0 | Day 5: 8
2.11 | PB01 | [FE] Code Register Function For Web Application | Trung | Done | 8 | 8 | 0 | 8 | 0 | Day 7: 8
2.12 | PB03 | [DB + BE] Create Database (UR_USER, UR_ROLE, USER_ROLE, UR_SESSION) and Mapping entities | Phuc | Done | 8 | 8 | 0 | 8 | 0 | Day 6: 8
2.13 | PB03 | [BE] Code Authorize Function (Personal User, Household, Local Authority, Admin) | Phuc | Done | 12 | 12 | 0 | 12 | 0 | Day 8: 12
2.14 | PB01 | [FE] Design Web layout (household, local authority, admin) | Phuc | Done | 8 | 8 | 0 | 8 | 0 | Day 11: 8
2.15 | PB02 | [FE] Design UX/UI Login Page For Web Application | Trung | Done | 2 | 2 | 0 | 3 | 1 | Day 7: 2
2.16 | PB02 | [FE] Code UX/UI Login Page For Web Application | Trung | Done | 2 | 2 | 0 | 3 | 1 | Day 7: 2
2.17 | PB02 | [FE] Code Login Function For Web Application | Trung | Done | 4 | 4 | 0 | 4 | 0 | Day 8: 4
2.18 | PB02 | [FE] Code Logout Function For Web Application | Trung | Done | 2 | 2 | 0 | 2 | 0 | Day 10: 2
2.19 | PB05 | [FE] Design UX/UI Edit Profile Page For Mobile Application | Ca | Done | 4 | 4 | 0 | 3 | -1 | Day 7: 4
2.20 | PB05 | [FE] Code UX/UI Edit Profile Page For Mobile Application | Ca | Done | 4 | 4 | 0 | 5 | 1 | Day 7: 4
2.21 | PB05 | [FE] Code Edit Profile Function For Mobile Application | Ca | Done | 3 | 3 | 0 | 4 | 1 | Day 8: 3
2.22 | PB05 | [BE] Code Update Profile API | Phuc | Done | 3 | 3 | 0 | 3 | 0 | Day 13: 3
2.23 | PB11 | [FE] Code Change Language For Mobile Application | Ca | Done | 12 | 12 | 0 | 15 | 3 | Day 14: 12
2.24 | PB13 | [AI] Process Training Data | Huy | Done | 26 | 26 | 0 | 26 | 0 | Day 6: 26
2.25 | PB13 | [AI] Train Model | Huy | Done | 26 | 26 | 0 | 26 | 0 | Day 13: 26
2.26 | PB07 | [FE] Code & Design UX/UI Change Password For Web Application | Trung | Done | 4 | 4 | 0 | 4 | 0 | Day 11: 3
2.27 | PB07 | [FE] Code & Design UX/UI Forget Password For Web Application | Trung | Done | 4 | 4 | 0 | 4 | 0 | Day 11: 4
2.28 | PB06 | [FE] Code & Design UX/UI Add New Local Authority For Web Application(Admin page) | Trung | Done | 8 | 8 | 0 | 8 | 0 | Day 14: 8
2.29 | PB02 | [BE] Code Login/Logout API | Phuc | Done | 12 | 12 | 0 | 15 | 3 | Day 14: 15
2.30 | PB01 | [BE] Code Mail Service | Phuc | Done | 4 | 4 | 0 | 4 | 0 | Day 14: 4
|  |  |  | Total | 207 | 207 | 0 | 211 | 4 | 20 | 11 | 4 | 4 | 8 | 38 | 20 | 19 | 0 | 2 | 15 | 0 | 29 | 35
|  |  |  | Burn down | [5 empty] | 187 | 176 | 172 | 168 | 160 | 122 | 102 | 83 | 83 | 81 | 66 | 66 | 37 | 2
|  |  |  | Burn up | [5 empty] | 20 | 31 | 35 | 39 | 47 | 85 | 105 | 124 | 124 | 126 | 141 | 141 | 170 | 205
|  |  |  | Ideal Burn down | [5 empty] | 192.2143 | 177.4286 | 162.6429 | 147.8571 | 133.0714 | 118.2857 | 103.5 | 88.7143 | 73.9286 | 59.1429 | 44.3571 | 29.5714 | 14.7857 | 0
|  |  |  | Ideal Burn up | [5 empty] | 0 | 14.7857 | 29.5714 | 44.3571 | 59.1429 | 73.9286 | 88.7143 | 103.5 | 118.2857 | 133.0714 | 147.8571 | 162.6429 | 177.4286 | 192.2143
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 3 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
3.1 | PB08 | [FE] Design UX/UI Survey Page For Mobile Application (Personal User) | Ca | Done | 8 | 8 | 0 | 10 | 2 | Day 4: 8
3.2 | PB08 | [FE] Code UX/UI Survey Page For Mobile Application (Personal User) | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 5: 8
3.3 | PB08 | [FE] Code Take Photo Function | Ca | Done | 4 | 4 | 0 | 4 | 0 | Day 6: 4
3.4 | PB08 | [FE] Code Location Base Function | Ca | Done | 8 | 8 | 0 | 7 | -1 | Day 8: 8
3.5 | PB08 | [FE] Code Automatic Fill Data Function | Ca | Done | 8 | 8 | 0 | 12 | 4 | Day 11: 8
3.6 | PB08 | [FE] Code Encrytion Image Function | Ca | Done | 8 | 8 | 0 | 5 | -3 | Day 12: 8
3.7 | PB08 | [FE] Code Submit Survey Function | Ca | Done | 8 | 8 | 0 | 10 | 2 | Day 13: 8
3.8 | PB08 | [BE] Code Location detection API | Phuc | Done | 10 | 10 | 0 | 8 | -2 | Day 5: 10
3.9 | PB08 | [DB + BE] Create table User_Survey and Mapping entity | Phuc | Done | 12 | 12 | 0 | 10 | -2 | Day 9: 12
3.10 | PB08 | [BE] Code Survey API | Phuc | Done | 18 | 18 | 0 | 18 | 0 | Day 12: 18
3.11 | PB14 | [FE] Design UX/UI Declare Page For Web Application (Household) | Trung | Done | 8 | 8 | 0 | 9 | 1 | Day 3: 8
3.12 | PB14 | [FE] Code UX/UI Declare Page For Web Application (Household) | Trung | Done | 8 | 8 | 0 | 8 | 0 | Day 4: 8
3.13 | PB14 | [BE] Code Household API | Phuc | Done | 8 | 8 | 0 | 8 | 0 | Day 13: 8
3.14 | PB15 | [FE] Design UX/UI Household Page | Trung | Done | 4 | 4 | 0 | 4 | 0 | Day 6: 4
3.15 | PB15 | [FE] Code UX/UI Household Page | Trung | Done | 12 | 12 | 0 | 16 | 4 | Day 7: 16
3.16 | PB06 | [BE] Code Admin API | Phuc | Done | 8 | 8 | 0 | 8 | 0 | Day 14: 8
3.17 | PB13 | [AI] Test And Retrain AI Model | Huy | Done | 45 | 45 | 0 | 45 | 0 | Day 10: 45
3.18 | PB13 | [AI] Write Pollution Detection API | Huy | Done | 8 | 8 | 0 | 8 | 0 | Day 12: 8
3.19 | PB08 | [FE] Write Detection Pollution Function | Ca | Done | 8 | 8 | 0 | 12 | 4 | Day 14: 8
|  |  |  | Total | 201 | 201 | 0 | 210 | 9 | 0 | 0 | 8 | 16 | 18 | 8 | 16 | 8 | 12 | 45 | 8 | 34 | 16 | 16
|  |  |  | Burn down | [5 empty] | 201 | 201 | 193 | 177 | 159 | 151 | 135 | 127 | 115 | 70 | 62 | 28 | 12 | -4
|  |  |  | Burn up | [5 empty] | 0 | 0 | 8 | 24 | 42 | 50 | 66 | 74 | 86 | 131 | 139 | 173 | 189 | 205
|  |  |  | Ideal Burn down | [5 empty] | 186.6429 | 172.2857 | 157.9286 | 143.5714 | 129.2143 | 114.8571 | 100.5 | 86.1429 | 71.7857 | 57.4286 | 43.0714 | 28.7143 | 14.3571 | 0
|  |  |  | Ideal Burn up | [5 empty] | 0 | 14.3571 | 28.7143 | 43.0714 | 57.4286 | 71.7857 | 86.1429 | 100.5 | 114.8571 | 129.2143 | 143.5714 | 157.9286 | 172.2857 | 186.6429
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 4 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
4.1 | PB12 | [FE] Redesign UX/UI View Finished Surveys Page For Mobile Application | Ca | Done | 8 | 8 | 0 | 10 | 2 | Day 1: 8
4.2 | PB12 | [FE] Update UX/UI View Finished Surveys Page For Mobile Application | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 2: 8
4.3 | PB12 | [FE] Update Function View Finished Surveys For Mobile Application | Ca | Done | 4 | 4 | 0 | 4 | 0 | Day 4: 4
4.4 | PB12 | [BE] Update View Finished Surveys API | Phuc | Done | 12 | 12 | 0 | 10 | -2 | Day 2: 12
4.5 | PB10 | [FE] Design UX/UI Accept/Decline New Village Page For Web Application | Trung | Done | 8 | 8 | 0 | 7 | -1 | Day 1: 8
4.6 | PB10 | [FE] Code UX/UI Accept/Decline New Village Page For Web Application | Trung | Done | 8 | 8 | 0 | 8 | 0 | Day 2: 8
4.7 | PB10 | [FE] Code Function Accept/Decline New Village For Web Application | Trung | Done | 8 | 8 | 0 | 9 | 1 | Day 6: 8
4.8 | PB09 | [FE] Redesign UX/UI Survey Page With Add New Village For Mobile Application (Personal User) | Ca | Done | 4 | 4 | 0 | 5 | 1 | Day 8: 4
4.9 | PB09 | [FE] Update UX/UI Survey Page With Add New Village For Mobile Application (Personal User) | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 9: 8
4.10 | PB09 | [FE] Update Submit Survey With New Village Function | Ca | Done | 8 | 8 | 0 | 7 | -1 | Day 10: 8
4.11 | PB14 | [BE] Code Dashboard API | Phuc | Done | 8 | 8 | 0 | 7 | -1 | Day 5: 8
4.12 | PB13 | [AI] Research Multi-Label Classification Machine Learning | Huy | Done | 26 | 26 | 0 | 26 | 0 | Day 7: 26
4.13 | PB13 | [AI] Crawl Training Data | Huy | Done | 26 | 26 | 0 | 26 | 0 | Day 14: 26
4.14 | PB11 | [FE] Update Change Language For Mobile Application | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 12: 8
4.15 | PB01 | [FE] ReDesign UX/UI Register Page For Mobile Application | Ca | Done | 4 | 4 | 0 | 4 | 0 | Day 13: 4
4.16 | PB01 | [FE] Update Register Function Using Mail For Mobile Application | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 14: 8
4.17 | PB14 | [FE] Design UX/UI Dashboard Page For Web Application | Trung | Done | 4 | 4 | 0 | 4 | 0 | Day 6: 4
4.18 | PB14 | [FE] Code UX/UI Dashboard Page For Web Application | Trung | Done | 8 | 8 | 0 | 8 | 0 | Day 7: 8
4.19 | PB01 | [BE] Update Register API Response Format | Phuc | Done | 12 | 12 | 0 | 10 | -2 | Day 9: 12
4.20 | PB08 | [DB] Crawl Craft Village Data (VILLAGE) | Trung | Done | 25 | 25 | 0 | 25 | 0 | Day 14: 25
|  |  |  | Total | 205 | 205 | 0 | 202 | -3 | 16 | 28 | 0 | 4 | 8 | 12 | 34 | 4 | 20 | 8 | 0 | 8 | 4 | 59
|  |  |  | Burn down | [5 empty] | 189 | 161 | 161 | 157 | 149 | 137 | 103 | 99 | 79 | 71 | 71 | 63 | 59 | 0
|  |  |  | Burn up | [5 empty] | 16 | 44 | 44 | 48 | 56 | 68 | 102 | 106 | 126 | 134 | 134 | 142 | 146 | 205
|  |  |  | Ideal Burn down | [5 empty] | 190.3571 | 175.7143 | 161.0714 | 146.4286 | 131.7857 | 117.1429 | 102.5 | 87.8571 | 73.2143 | 58.5714 | 43.9286 | 29.2857 | 14.6429 | 0
|  |  |  | Ideal Burn up | [5 empty] | 0 | 14.6429 | 29.2857 | 43.9286 | 58.5714 | 73.2143 | 87.8571 | 102.5 | 117.1429 | 131.7857 | 146.4286 | 161.0714 | 175.7143 | 190.3571
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 4 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 5 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
5.1 | PB13 | [AI] Process Training Data | Huy | Done | 20 | 20 | 0 | 20 | 0 | Day 6: 20
5.2 | PB13 | [AI] Train New Model | Huy | Done | 20 | 20 | 0 | 20 | 0 | Day 10: 20
5.3 | PB13 | [AI] Write Pollution Detection API | Huy | Done | 12 | 12 | 0 | 10 | -2 | Day 11: 12
5.4 | PB08 | [FE] Write Detection Pollution Function | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 12: 8
5.5 | PB08 | [FE] Code Submit Survey With New Village Function | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 14: 8
5.6 | PB08 | [FE] Add Scroll Up Button For All Page | Phuc | Done | 8 | 8 | 0 | 8 | 0 | Day 4: 8
5.7 | PB02 | [FE] Redesign UX/UI Home Page For Mobile Application | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 5: 8
5.8 | PB02 | [FE] Update UX/UI Home Page For Mobile Application | Ca | Done | 12 | 12 | 0 | 8 | -4 | Day 6: 12
5.9 | PB08 | [DB] Crawl Craft Village Data (VILLAGE) | Trung | Done | 40 | 40 | 0 | 40 | 0 | Day 14: 40
5.10 | PB08 | [FE] Update Location Base Function | Ca | Done | 8 | 8 | 0 | 7 | -1 | Day 9: 8
5.11 | PB08 | [BE] Update Location Base API | Phuc | Done | 8 | 8 | 0 | 8 | 0 | Day 8: 8
5.12 | PB15 | [FE] Redesign UX/UI Household Page For Web Application | Trung | Done | 8 | 8 | 0 | 6 | -2 | Day 4: 8
5.13 | PB15 | [FE] Update UX/UI Household Page For Web Application | Trung | Done | 8 | 8 | 0 | 8 | 0 | Day 5: 8
5.14 | PB08 | [BE] Update Submit Survey API | Phuc | Done | 8 | 8 | 0 | 7 | -1 | Day 12: 8
5.15 | PB09 | [FE] Redesign UX/UI Survey Page For Mobile Application (Personal User) | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 10: 8
5.16 | PB09 | [FE] Update UX/UI Survey Page For Mobile Application (Personal User) | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 11: 8
5.17 | PB11 | [FE] Update Change Language For Mobile Application | Ca | Done | 8 | 8 | 0 | 8 | 0 | Day 3: 8
|  |  |  | Total | 200 | 200 | 0 | 190 | -10 | 0 | 0 | 8 | 16 | 16 | 32 | 0 | 8 | 8 | 28 | 20 | 16 | 0 | 48
|  |  |  | Burn down | [5 empty] | 200 | 200 | 192 | 176 | 160 | 128 | 128 | 120 | 112 | 84 | 64 | 48 | 48 | 0
|  |  |  | Burn up | [5 empty] | 0 | 0 | 8 | 24 | 40 | 72 | 72 | 80 | 88 | 116 | 136 | 152 | 152 | 200
|  |  |  | Ideal Burn down | [5 empty] | 185.7143 | 171.4286 | 157.1429 | 142.8571 | 128.5714 | 114.2857 | 100 | 85.7143 | 71.4286 | 57.1429 | 42.8571 | 28.5714 | 14.2857 | 0
|  |  |  | Ideal Burn up | [5 empty] | 0 | 14.2857 | 28.5714 | 42.8571 | 57.1429 | 71.4286 | 85.7143 | 100 | 114.2857 | 128.5714 | 142.8571 | 157.1429 | 171.4286 | 185.7143
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 5 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On
1 | I have a hardware problem when try to run the emulator for the project (Low on memory and storage) | Ca | 2022-09-01 |  |  | Ca | Done | Buy hardware upgrade form the shop | 2022-09-02
2 | My computer broke and I need two days for repair | Huy | 2022-09-04 |  |  | Huy | Done | Bring the computer to the repair shop | 2022-09-06
3 | I still haven't got the database software to work with | Trung | 2022-09-03 |  |  | Phuc | Done | Use a remote software to help install the database software | 2022-09-03
4 | I can't contact the group members immediately when I need to ask about problems in the project | Phuc | 2022-09-09 |  |  | Ca | Done | Set up a meeting with the team and agree that we will have a daily meeting | 2022-09-10
5 | I can't keep up with the daily meeting because I still have to go to school and the internship | Huy | 2022-09-21 |  |  | Ca | Done | Set up a meeting with the team and agree that we will have a meeting every two or three days and the schedule will be set up in advance | 2022-09-21
6 | I struggling to understand how to use the API and would like someone to help me out | Trung | 2022-09-22 |  |  | Phuc | Done | The onwer will set up a meeting with the member for support | 2022-09-22
7 | I don't have an Android phone to test the mobile application | Ca | 2022-10-15 |  |  | Ca | Done | Buy an Android phone for the shop | 2022-10-17

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks
1 | 2 |  | Huy |  |  | Let daily meeting become discussions. Keep them short.
1 | 2 |  | Ca |  |  | Having conversations via email and not in the task.
1 | 2 |  | Phuc |  | Attend meeting on time.
2 | 3 |  | Huy | We completed the user stories we set out to do.
2 | 3 |  | Ca |  |  | We didn't finish all the user stories.
2 | 3 |  | Trung | We should start doing individual code reviews as we go.
2 | 3 |  | Phuc |  | We should increase the amount we communicate as a team.
3 | 4 |  | Ca | We were able to demo a working product to the mentor.
3 | 4 |  | Phuc |  | We should continue having regular demos with the mentor.
3 | 4 |  | Trung | Collect mentor feedback on new features.
3 | 4 |  | Huy | Going through the entire Bug log.
3 | 4 |  | Trung |  | We should continue working as a team.
3 | 4 |  | Phuc | Review stories with mentor before implementation.
4 | 5 |  | Trung |  | Great teamwork.

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms