## AcceptDecline New Village onWeb
Module Code | Accept/Decline New Village page on Website
Tester
Pre-condition | Internet is connected, Login successful, Accept/Decline page is loaded
Pass | Fail | Number of Test case
9 | 0 | 9
ID | Test Case Description | Test Case Produre | Excepted Output | Actual Result | Test Result | Test Date
TC01 | Check Accept new village success | Click on "✓" button | Accept new village | Accept new village | Pass | 2022-11-03
TC02 | Check Decline new village success | Click on "X" button | Decline new village | Decline new village | Pass | 2022-11-03
TC03 | Check Create a new village success | 1. Select Ward 2. Enter the name of craft village 3. Enter the longtitude 4. Enter the latitude 5. Enter the description about craft village 6. Click on "Tạo" button | Create a new village to database | Create a new village to database | Pass | 2022-11-03
TC04 | Declare empty ward | 1. Unselect Ward 2. Enter the name of craft village 3. Enter the longtitude 4. Enter the latitude 5. Enter the description about craft village 6. Click on "Tạo" button | Display Error Message "Vui lòng nhập đầy đủ thông tin!" | Display Error Message "Vui lòng nhập đầy đủ thông tin!" | Pass | 2022-11-03
TC05 | Declare name of craft village with special character | 1. Select Ward 2. Enter the name of craft village with special characters 3. Enter the longtitude 4. Enter the latitude 5. Enter the description about craft village 6. Click on "Tạo" button | Create a new village to database | Create a new village to database | Pass | 2022-11-03
TC06 | Declare invalid longtitude | 1. Select Ward 2. Enter the name of craft village 3. Enter the invalid longtitude 4. Enter the latitude 5. Enter the description about craft village 6. Click on "Tạo" button | Display Error Message "Vui lòng nhập đầy đủ thông tin!" | Display Error Message "Vui lòng nhập đầy đủ thông tin!" | Pass | 2022-11-03
TC07 | Declare invalid latitude | 1. Select Ward 2. Enter the name of craft village 3. Enter the longtitude 4. Enter the invalid latitude 5. Enter the description about craft village 6. Click on "Tạo" button | Display Error Message "Vui lòng nhập đầy đủ thông tin!" | Display Error Message "Vui lòng nhập đầy đủ thông tin!" | Pass | 2022-11-03
TC08 | Declare empty description about craft village | 1. Select Ward 2. Enter the name of craft village 3. Enter the longtitude 4. Enter the latitude 5. Leave the description about craft village blank 6. Click on "Tạo" button | Display Error Message "Vui lòng nhập đầy đủ thông tin!" | Display Error Message "Vui lòng nhập đầy đủ thông tin!" | Pass | 2022-11-03
TC09 | Declare empty name of craft village | 1. Select Ward 2. Leave the box to the name of craft village blank 3. Enter the longtitude 4. Enter the latitude 5. Enter the description about craft village 6. Click on "Tạo" button | Display Error Message "Vui lòng nhập đầy đủ thông tin!" | Display Error Message "Vui lòng nhập đầy đủ thông tin!" | Pass | 2022-11-03

## Dashboard Page on Web
Module Code | Dashboard page on Website
Tester
Pre-condition | Internet is connected, Login successful, Accept/Decline page is loaded
Pass | Fail | Number of Test case
2 | 0 | 2
ID | Test Case Description | Test Case Produre | Excepted Output | Actual Result | Test Result | Test Date
TC01 | Check dashboard | 1. Click on "Village" button 2. Click on "New Village" 3. Click on "Dashboard" | Switch to Accept/Decline Homepage Page | Switch to Accept/Decline Homepage Page | Pass | 2022-11-03
TC02 | Check switch to Accept/Decline Page | 1. Click on "Village" button 2. Click on "New Village" | Switch to Accept/Decline Page | Switch to Accept/Decline Page | Pass | 2022-11-03