## Product Backlog
Product Backlog
*Priority: The higher the more important
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Report Feature | Local Authority Household | Fill report form | I can inform problem to development team | - Allow user to report error to the development team |  | 3 |  |  |  | 2 | 30 |  |  | Done
PB02 | Household Survey Feature | Household | Fill my production situation form | Local authority can manage my production situation | - Allow user to provide craft village production information |  | 3 |  |  |  | 1, 2, 5 | 100 |  |  | Done
PB03 | Dashboard Feature | Local Authority | View villages production situation and personal user surveys | I can manage pollution situation | - Allow user to view craft village status and submitted survey |  | 2 |  |  |  | 2 | 20 |  |  | Done
PB04 | Pollution Prediction AI | Household Authority | Have an AI with the ability to predict the pollution types of a craft village from production information automatically and acurately | when combie with submitted pollution information we will know with craft village that have the conflict information about the production information | - Allow user to submit production information and the AI will gave the prediction about the types of pollution that the craft village will be facing |  | 3 |  |  |  | 3, 4 | 400 |  |  | Done
PB05 | Edit Village Feature | Local Authority | Change village information | I can correct and update village |  |  | 3 |  |  |  | 3 | 30 |  |  | Done
PB06 | Fake Training Data | Admin | Generate new model using household data | System can detect pollution more correctly |  |  | 3 |  |  |  | 4 | 200 |  |  | Done
PB07 | Auto Update Village State | Admin | System updates village state | I can check conflicting data |  |  | 3 |  |  |  | 5 | 30 |  |  | Done
PB08 | Download Data Set | Admin | Download village data set | I can build enhanced model in future |  |  | 3 |  |  |  | 5 | 30 |  |  | Done
PB09 | Notification Feature | Local Authority | Know if data is conflicting | I can check what problem occurs |  |  | 3 |  |  |  | 5 | 30 |  |  | Done
PB10 | Register | Household | Create an account | I can login with my own account to access the mobile application/web application | - Username must not contain spaces and not be accented - Password must be >= 6 characters |  | 3 |  |  |  | 1 | 30 |  |  | Done
PB11 | Authenticate | Household Authority Admin | Login/Logout to web application | I can start to provide the information about the craft village/view craft village's status | - Login with registed account |  | 3 |  |  |  | 1 | 100 |  |  | Done
PB12 | Password Recovery | Household | Recover password when forgot | I can change my password into the new one and get my account back | - Use the code that sent to the account's email which is registered in the profile to change the new password |  | 2 |  |  |  | 1 | 20 |  |  | Done
PB13 | Create Local Authority Account | Admin | Create an local authority account | I can provide the account to the local authority user to manage their local craft village | - Allow the admin to create the a local authority account - Login with registed account |  | 2 |  |  |  | 2 | 30 |  |  | Done
PB14 | Improve Pollution Detection AI | Personal User | Have an AI with the ability to detect the pollution types from an image automatically and acurately | The application can detect pollutions types automatically with a quick and accureate respone | - Allow user to submit pollution photo and the AI will detect pollution types then sent back to the application |  | 3 |  |  |  | 1, 2 | 200 |  |  | Done
PB15 | Pollution Fillter | Local Authority | Have an Pollution Fillter to sort out the pollution that I need | I can see specific pollution that I need to see | - Allow user to fillter out the types of pollution that they want to see |  | 2 |  |  |  | 5 | 30 |  |  | Done
PB16 | Publish Application | Personal User | Have the application on Google Store | People can download and use it | - Application publish to store |  | 3 |  |  |  | 1, 2, 5 | 30 |  |  | Done
PB17 | Change Language | Personal User | Change the language of the mobile | The application language change from Vietnamese to English and vice versa | - Allow users to change the language of the application from Vietnamese to English and vice versa |  | 1 |  |  |  | 1, 2 | 20 |  |  | Done
PB18 | Deploy Web Application to Online Server | Household Authority Admin | Use the web application on a real server | I can access the web application and it's functions anywhere | - Allow users to access the web application throught ip or domain name (online server) |  | 3 |  |  |  | 1, 3, 4, 5 | 30 |  |  | Done
PB19 | Change Password | Household Authority Admin | Change my old password into a new password | Next time I can login using my new password and protect my account in case of password leak | - Allow user to click "Thay đổi mật khẩu" and change their current password to a new password |  | 3 |  |  |  | 1 | 30 |  |  | Done
PB20 | GPS Tags to Image | Personal User | Attach GPS tags to image | The image can contant the GPS location of pollutions | - Attach GPS tags to image |  | 3 |  |  |  | 2, 3, 4 | 30 |  |  | Done
PB21 | Authorize | Personal User Household Authority Admin | Login/Logout according to the role that has been registed | I can perform the task correctly according to the role | - Login with registed account and perform task according to the registed role |  | 3 |  |  |  | 2 | 100 |  |  | Done
PB22 | Accept/Decline/Add New Village | Local Authority | Accept/Decline a new village that has been submit by a personal user | I can protect the integrity of the craft village data from fault information | - Allow user to accepct or decline the new village that submitted by a personal user and that village belong to their management |  | 3 |  |  |  | 2 | 20 |  |  | Done
Note on M7: ====== ID#AAAAeu_Dblk jan samuelsson (2022-08-23 14:14:25) Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.

## Main
Project | [5 empty] | Sprint Plan |  | Project Craft Village Pollution Monitor System
Id | Description | Start | End | Status | Remarks | Sprint # | Start | End | Status | Work / Estimates Committed | Work spent Delivered | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 | 2023-03-01 | 2023-03-14 | Complete
[6 empty] | 2 | 2023-03-15 | 2023-03-28 | Complete
[6 empty] | 3 | 2023-03-30 | 2023-04-12 | Complete
[6 empty] | 4 | 2023-04-14 | 2023-04-27 | Complete
[6 empty] | 5 | 2023-04-29 | 2023-05-12 | Complete
Formulas:
End = [Start]+13
End = [Start]+14-1
Start = [End, row above]+1
Start = [End, row above]+1+1

## Sprint 1 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1.1 | PB10 | [FE] Design Web layout | Phuc | Done | 25 | 25 | 0 | 20 | -5 | Day 4: 25
1.2 | PB10 | [FE] Design UX/UI Login Page For Web Application | Trung | Done | 15 | 15 | 0 | 15 | 0 | Day 3: 15
1.3 | PB10 | [FE] Design UX/UI Home Page For Web Application | Trung | Done | 15 | 15 | 0 | 15 | 0 | Day 5: 15
1.4 | PB10 | [FE] Code UX/UI Login Page For Web Application | Nhan | Done | 10 | 10 | 0 | 10 | 0 | Day 1: 10
1.5 | PB10 | [FE] Code UX/UI Home Page For Web Application | Nhan | Done | 10 | 10 | 0 | 7 | -3 | Day 2: 10
1.6 | PB11 | [FE] Code Login Function For Web Application | Phuc | Done | 8 | 8 | 0 | 5 | -3 | Day 5: 8
1.7 | PB11 | [FE] Code Logout Function For Web Application | Phuc | Done | 3 | 3 | 0 | 2 | -1 | Day 5: 3
1.8 | PB10 | [FE] Design UX/UI Register Page For Web Application | Trung | Done | 15 | 15 | 0 | 13 | -2 | Day 6: 15
1.9 | PB10 | [FE] Code UX/UI Register Page For Web Application | Nhan | Done | 15 | 15 | 0 | 10 | -5 | Day 3: 15
1.10 | PB10 | [FE] Code Register Function For Web Application | Phuc | Done | 25 | 25 | 0 | 15 | -10 | Day 6: 25
1.11 | PB14 | [AI] Research Method To Improve AI | Huy | Done | 30 | 30 | 0 | 30 | 0 | Day 4: 30
1.12 | PB14 | [AI] Crawl Data For Improve AI | Huy | Done | 30 | 30 | 0 | 30 | 0 | Day 11: 30
1.13 | PB17 | [FE] Code Change Language For Mobile Application | Ca | Done | 25 | 25 | 0 | 30 | 5 | Day 5: 25
1.14 | PB16 | [FE] Research Method To Publish Application | Ca | Done | 25 | 25 | 0 | 15 | -10 | Day 8: 25
1.15 | PB16 | [FE] Config Application For Publish Application | Ca | Done | 15 | 15 | 0 | 10 | -5 | Day 10: 15
1.16 | PB16 | [FE] Publish Application To Google Play | Ca | Done | 10 | 10 | 0 | 8 | -2 | Day 12: 10
1.17 | PB02 | [BE + DB] Create Question, Question Answer, Household Survey Entity | Phuc | Done | 10 | 10 | 0 | 8 | -2 | Day 8: 10
1.18 | PB12 | [FE] Code & Design UX/UI Change Password For Web Application | Trung | Done | 15 | 15 | 0 | 12 | -3 | Day 9: 15
1.19 | PB19 | [FE] Code & Design UX/UI Forget Password For Web Application | Phuc | Done | 15 | 15 | 0 | 9 | -6 | Day 12: 15
1.20 | PB18 | [BD] Change Oracle Database to MySQL Database | Nhan | Done | 25 | 25 | 0 | 27 | 2 | Day 14: 25
|  |  |  | Total | 341 | 341 | 0 | 291 | -50 | 0 | 10 | 10 | 30 | 55 | 51 | 40 | 0 | 35 | 15 | 15 | 30 | 25 | 0 | 25
|  |  |  | Burn down | [5 empty] | 341 | 331 | 321 | 291 | 236 | 185 | 145 | 145 | 110 | 95 | 80 | 50 | 25 | 25 | 0
|  |  |  | Ideal Burn down | [5 empty] | 341 | 316.6429 | 292.2857 | 267.9286 | 243.5714 | 219.2143 | 194.8571 | 170.5 | 146.1429 | 121.7857 | 97.4286 | 73.0714 | 48.7143 | 24.3571 | 0
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart

## Sprint 2 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
2.1 | PB13 | [FE] Code & Design UX/UI Add New Local Authority For Web Application(Admin page) | Trung | Done | 15 | 15 | 0 | 10 | -5 | Day 2: 15
2.2 | PB21 | [FE] Design Web layout (Household, Local Authority, Admin) | Phuc | Done | 20 | 20 | 0 | 18 | -2 | Day 3: 20
2.3 | PB01 | [FE] Design UX/UI Report Form For Web Application | Phuc | Done | 10 | 10 | 0 | 8 | -2 | Day 4: 10
2.4 | PB01 | [FE] Code Report API | Phuc | Done | 15 | 15 | 0 | 12 | -3 | Day 5: 15
2.5 | PB01 | [FE] Code Report Logic For Web Application | Nhan | Done | 15 | 15 | 0 | 17 | 2 | Day 2: 15
2.6 | PB02 | [BE] Code Question Api | Phuc | Done | 20 | 20 | 0 | 22 | 2 | Day 7: 20
2.7 | PB02 | [BE] Code Question Answer Api | Phuc | Done | 10 | 10 | 0 | 12 | 2 | Day 9: 10
2.8 | PB02 | [FE] Design Household Survey | Nhan | Done | 5 | 5 | 0 | 4 | -1 | Day 5: 5
2.9 | PB02 | [FE] Code Declare Household Survey | Nhan | Done | 10 | 10 | 0 | 15 | 5 | Day 6: 10
2.10 | PB22 | [FE] Design UX/UI Accept/Decline New Village Page For Web Application | Trung | Done | 5 | 5 | 0 | 6 | 1 | Day 4: 10
2.11 | PB22 | [FE] Code UX/UI Accept/Decline New Village Page For Web Application | Phuc | Done | 10 | 10 | 0 | 8 | -2 | Day 10: 5
2.12 | PB03 | [FE] Design UX/UI Dashboard Page For Web Application | Nhan | Done | 5 | 5 | 0 | 6 | 1 | Day 7: 5
2.13 | PB03 | [FE] Code UX/UI Dashboard Page For Web Application | Nhan | Done | 10 | 10 | 0 | 7 | -3 | Day 9: 10
2.14 | PB03 | [FE] Design UX/UI Declare Page For Web Application (Household) | Trung | Done | 5 | 5 | 0 | 6 | 1 | Day 5: 5
2.15 | PB03 | [FE] Code UX/UI Declare Page For Web Application (Household) | Phuc | Done | 10 | 10 | 0 | 11 | 1 | Day 12: 10
2.16 | PB14 | [AI] Retrain AI Model | Huy | Done | 30 | 30 | 0 | 35 | 5 | Day 5: 30
2.17 | PB14 | [AI] Research Deploy Model To Server | Huy | Done | 20 | 20 | 0 | 17 | -3 | Day 11: 20
2.18 | PB14 | [AI] Deploy Model To Server | Huy | Done | 5 | 5 | 0 | 3 | -2 | Day 12: 5
2.19 | PB17 | [FE] Update Change Language Function | Ca | Done | 30 | 30 | 0 | 24 | -6 | Day 8: 30
2.20 | PB20 | [FE] Update Craft Page | Ca | Done | 20 | 20 | 0 | 15 | -5 | Day 12: 20
2.21 | PB16 | [FE] Deploy New Version To Store | Ca | Done | 2 | 2 | 0 | 3 | 1 | Day 14: 2
|  |  |  | Total | 272 | 272 | 0 | 259 | -13 | 0 | 0 | 30 | 20 | 20 | 55 | 10 | 25 | 30 | 20 | 5 | 20 | 35 | 0 | 2
|  |  |  | Burn down | [5 empty] | 272 | 272 | 242 | 222 | 202 | 147 | 137 | 112 | 82 | 62 | 57 | 37 | 2 | 2 | 0
|  |  |  | Ideal Burn down | [5 empty] | 272 | 252.5714 | 233.1429 | 213.7143 | 194.2857 | 174.8571 | 155.4286 | 136 | 116.5714 | 97.1429 | 77.7143 | 58.2857 | 38.8571 | 19.4286 | 0
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart

## Sprint 3 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
3.1 | PB05 | [FE] Design Edit Village Page | Phuc | Done | 20 | 20 | 0 | 18 | -2 | Day 4: 20
3.2 | PB05 | [FE] Implement Map | Nhan | Done | 30 | 30 | 0 | 40 | 10 | Day 9: 30
3.3 | PB05 | [FE] Code Edit Village Feature | Phuc | Done | 20 | 20 | 0 | 25 | 5 | Day 6: 20
3.4 | PB05 | [BE] Code Update Village API | Phuc | Done | 20 | 20 | 0 | 15 | -5 | Day 6: 20
3.5 | PB04 | [AI] Research Prediction AI | Huy | Done | 30 | 30 | 0 | 35 | 5 | Day 6: 30
3.6 | PB04 | [AI] Research API For Prediction AI | Huy | Done | 30 | 30 | 0 | 32 | 2 | Day 14: 30
3.7 | PB04 | [AI] Create Data For Prediction AI | Trung | Done | 60 | 60 | 0 | 70 | 10 | Day 14: 60
3.8 | PB20 | [FE] Research Image Standard And Tags | Ca | Done | 30 | 30 | 0 | 32 | 2 | Day 6: 30
3.9 | PB20 | [FE] Attach GPS Tags For Image | Ca | Done | 30 | 30 | 0 | 25 | -5 | Day 13: 30
3.10 | PB18 | [BE] Deploy Backend To Server | Nhan | Done | 30 | 30 | 0 | 35 | 5 | Day 14: 30
|  |  |  | Total | 300 | 300 | 0 | 327 | 27 | 0 | 0 | 0 | 0 | 20 | 0 | 100 | 0 | 0 | 30 | 0 | 0 | 0 | 30 | 120
|  |  |  | Burn down | [5 empty] | 300 | 300 | 300 | 300 | 280 | 280 | 180 | 180 | 180 | 150 | 150 | 150 | 150 | 120 | 0
|  |  |  | Ideal Burn down | [5 empty] | 300 | 278.5714 | 257.1429 | 235.7143 | 214.2857 | 192.8571 | 171.4286 | 150 | 128.5714 | 107.1429 | 85.7143 | 64.2857 | 42.8571 | 21.4286 | 0
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart

## Sprint 4 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
4.1 | PB06 | [BE + DB] Code DataSet Entity | Phuc | Done | 20 | 20 | 0 | 15 | -5 | Day 3: 20
4.2 | PB04 | [AI] Create Data For Prediction AI | Trung | Done | 60 | 60 | 0 | 80 | 20 | Day 14: 60
4.3 | PB06 | [BE] Code DataSet API | Phuc | Done | 20 | 20 | 0 | 16 | -4 | Day 6: 20
4.4 | PB06 | [DB] Generate Store Procedure Update DataSet | Phuc | Done | 30 | 30 | 0 | 25 | -5 | Day 10: 30
4.5 | PB06 | [AI] Process Data For AI Trainning | Nhan | Done | 20 | 20 | 0 | 23 | 3 | Day 2: 20
4.6 | PB04 | [AI] Train Prediction AI Model | Huy | Done | 30 | 30 | 0 | 30 | 0 | Day 5: 30
4.7 | PB04 | [AI] Write API For Prediction AI | Huy | Done | 25 | 25 | 0 | 20 | -5 | Day 9: 25
4.8 | PB18 | [AI] Deploy Model To Server | Huy | Done | 5 | 5 | 0 | 3 | -2 | Day 10: 5
4.9 | PB05 | [BE] Layout Survey Marker on Map | Nhan | Done | 15 | 15 | 0 | 13 | -2 | Day 4: 15
4.10 | PB20 | [FE] Attach GPS Tags For Image Using EXIF Standard | Ca | Done | 30 | 30 | 0 | 32 | 2 | Day 6: 30
4.11 | PB20 | [FE] Update Craft Page | Ca | Done | 15 | 15 | 0 | 12 | -3 | Day 10: 15
4.12 | PB05 | [FE] View Sumitted Survey | Nhan | Done | 20 | 20 | 0 | 15 | -5 | Day 7: 20
4.13 | PB18 | [BE] Deploy New Backend Version To Server | Nhan | Done | 15 | 15 | 0 | 12 | -3 | Day 11: 15
|  |  |  | Total | 305 | 305 | 0 | 296 | -9 | 0 | 0 | 20 | 20 | 15 | 30 | 50 | 20 | 0 | 25 | 50 | 15 | 0 | 0 | 60
|  |  |  | Burn down | [5 empty] | 305 | 305 | 285 | 265 | 250 | 220 | 170 | 150 | 150 | 125 | 75 | 60 | 60 | 60 | 0
|  |  |  | Ideal Burn down | [5 empty] | 305 | 283.2143 | 261.4286 | 239.6429 | 217.8571 | 196.0714 | 174.2857 | 152.5 | 130.7143 | 108.9286 | 87.1429 | 65.3571 | 43.5714 | 21.7857 | 0
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 4 Reports
Reports & Dashboards
Burn down Chart

## Sprint 5 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
5.1 | PB07 | [AI] Generate Training Data From Json | Huy | Done | 30 | 30 | 0 | 30 | 0 | Day 5: 30
5.2 | PB07 | [AI] Implement New Model | Huy | Done | 30 | 30 | 0 | 30 | 0 | Day 12: 30
5.3 | PB07 | [FE] Code Update Required Question Feature | Nhan | Done | 20 | 20 | 0 | 25 | 5 | Day 4: 20
5.4 | PB08 | [BE] Code Get Data Set API | Phuc | Done | 20 | 20 | 0 | 15 | -5 | Day 2: 20
5.5 | PB08 | [BE] Code Call Predict API With Data Set | Phuc | Done | 20 | 20 | 0 | 12 | -8 | Day 8: 20
5.6 | PB02 | [BE] Refactor Question and Question Answer and Household Survey | Phuc | Done | 10 | 10 | 0 | 15 | 5 | Day 9: 10
5.7 | PB08 | [FE] Code Download Data Set Feature For Web Application | Nhan | Done | 20 | 20 | 0 | 18 | -2 | Day 8: 20
5.8 | PB09 | [BE] Code Notification API | Phuc | Done | 10 | 10 | 0 | 12 | 2 | Day 10: 10
5.9 | PB09 | [FE] Code Notification Feature | Nhan | Done | 20 | 20 | 0 | 25 | 5 | Day 12: 20
5.10 | PB18 | [AI] Deploy Model To Server | Huy | Done | 5 | 5 | 0 | 6 | 1 | Day 13: 5
5.11 | PB18 | [BE] Deploy Backend To Server | Nhan | Done | 15 | 15 | 0 | 10 | -5 | Day 14: 15
5.12 | PB16 | [FE] Code Fillter For Pollution Types | Phuc | Done | 15 | 15 | 0 | 12 | -3 | Day 13: 15
5.13 | PB15 | [FE] Deploy New Version To Store | Ca | Done | 3 | 3 | 0 | 2 | -1 | Day 1: 3
|  |  |  | Total | 218 | 218 | 0 | 212 | -6 | 0 | 3 | 20 | 0 | 20 | 30 | 0 | 0 | 40 | 10 | 10 | 0 | 50 | 20 | 15
|  |  |  | Burn down | [5 empty] | 218 | 215 | 195 | 195 | 175 | 145 | 145 | 145 | 105 | 95 | 85 | 85 | 35 | 15 | 0
|  |  |  | Ideal Burn down | [5 empty] | 218 | 202.4286 | 186.8571 | 171.2857 | 155.7143 | 140.1429 | 124.5714 | 109 | 93.4286 | 77.8571 | 62.2857 | 46.7143 | 31.1429 | 15.5714 | 0
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 5 Reports
Reports & Dashboards
Burn down Chart

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On
1 | Don't have Android phone to test application | Ca | 2023-03-01 |  |  | Ca | Done | Buy a phone from the shop | 2023-03-03
2 | Computer broke and I need three days for repair | Trung | 2023-03-09 |  |  | Trung | Done | Bring the computer to the repair shop | 2023-03-11
3 | I still haven't got the database software to work with | Trung | 2022-09-03 |  |  | Phuc | Done | Use a remote software to help install the database software | 2022-09-03
4 | I can't contact the group members immediately when I need to ask about problems in the project | Phuc | 2023-04-01 |  |  | Ca | Done | Set up a meeting with the team and agree that we will have a daily meeting | 2023-04-01
5 | I can't keep up with the daily meeting because I still have to go to school and the internship | Huy | 2023-04-01 |  |  | Ca | Done | Set up a meeting with the team and agree that we will have a meeting every two or three days and the schedule will be set up in advance | 2023-04-03
6 | I struggling to understand how to use the workflow and would like someone to help me out | Ca | 2023-04-18 |  |  | Phuc | Done | The onwer will set up a meeting with the member for support | 2023-04-19
7 | I don't have an Android phone to test the mobile application | Nhan | 2023-05-01 |  |  | Ca | Done | Lend him the Android phone | 2023-05-03
8 | AWS server shutdown for no reason | Ca | 2023-03-04 |  |  | Nhan | Done | Rent VPS server | 2023-03-06

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks
1 | 2 |  | Huy |  |  | Let daily meeting become discussions. Keep them short.
1 | 2 |  | Ca |  |  | Having conversations via email and not in the task.
1 | 2 |  | Phuc |  | Attend meeting on time.
2 | 3 |  | Huy | We completed the user stories we set out to do.
2 | 3 |  | Ca |  |  | We didn't finish all the user stories.
2 | 3 |  | Trung | We should start doing individual code reviews as we go.
2 | 3 |  | Phuc |  | We should increase the amount we communicate as a team.
3 | 4 |  | Ca | We were able to demo a working product to the mentor.
3 | 4 |  | Phuc |  | We should continue having regular demos with the mentor.
3 | 4 |  | Nhan | Collect mentor feedback on new features.
3 | 4 |  | Huy | Going through the entire Bug log.
3 | 4 |  | Trung |  | We should continue working as a team.
3 | 4 |  | Phuc | Review stories with mentor before implementation.
4 | 5 |  | Nhan |  | Great teamwork.

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms